## trade fair participation
Checklist domestic trade fair participation
What | Months Before/after start of fair | Who | When (real date dependent upon trade fair date
Preparation
Define corporate objectives and expectations | 12 to 9 months
New products or services ready for use at the beginning of the fair? | 12 to 9 months
Check economic situation, sales possibilities and distribution | 12 to 9 months
Cost expectations, return on investment | 12 to 9 months
Company decision on trade fair participation | 12 to 9 months
Budget approval | 12 to 9 months
Appoint project management/company team | 12 to 9 months
Internal coordination | 12 to 9 months
Request trade fair documentation, determine stand size, registration, reserve/book accommodation | 9 to 6 months
Selection of exhibits | 9 to 6 months
Stand planning | 9 to 6 months
Selection of stand construction company | 6 to 3 months
Outdoor advertising, advertising gifts | 6 to 3 months
Briefing stand construction company | 6 to 3 months
Commissioning stand construction company | 6 to 3 months
Entry in trade fair catalogue and supporting media | 6 to 3 months
Presentation of proposal by stand construction company | 6 to 3 months
Select external staff / hostesses | 6 to 3 months
Dress code / uniforms | 6 to 3 months
Commission catalogues and brochures | 3 to 1 months
Order communication services, electricity, water for trade fair stand | 3 to 1 months
Decide on stand personnel | 3 to 1 months
Graphics for the trade fair stand | 3 to 1 months
Mailings to customers / invitations | 3 to 1 months
Start briefing of stand team | 3 to 1 months
Name badges | 3 to 1 months
Press activities | 3 to 1 months
Start of trade fair
Stand hand-over by stand construction company | Trade fair
Visitor survey | Trade fair
Success controls | Trade fair
Observation of competitors | Trade fair
Follow-up
Orderly dismantling and return transport | 0 to 1 month
Analysis of participation | 0 to 1 month
Achievement of corporate objectives? | 0 to 1 month
Follow-up / customer contacts | 0 to 1 month
Cost registration | 2 months
AUMA Trade Fair Benefit Check
Consequences for the future | 2 months
Determine return on investment | 2 months